## Marketing Material
| Projects Overall Target | Currently Achieved | YEAR 1 - 2025/2026 | [11 empty] | YEAR 2 - 2026/2027 | [11 empty] | YEAR 3 - 2027/2028
|  |  | M1 - JAN | M2 - FEB | M3 - MAR | M4 - APR | M5- MAY | M6- JUN | M7 - JUL | M8 - AUG | M9 - SEPT | M10 - OCT | M11 - NOV | M12 - DEC | M13 -JAN | M14 - FEB | M15 - MAR | M16 -APR | M17 - MAY | M18 - JUN | M19 -JUL | M20 -AUG | M21 - SEP | M22 - OCT | M23- NOV | M24 - DEC | M25 -JAN | M26 - FEB | M27-MAR | M28- APR | M29 - MAY | M30 - JUN | M31- JUL | M32 - AUG | M33 - SEPT | M34- OCT | M35 - NOV | M36 - DEC
[C7] Marketing pack and promotional press kit | 1 Rollup | 1 |  |  | done
| 1 Brochure | 1 |  |  | done
| 1 Banner | 1 |  |  | cluster banner
| 2 Factsheets (interim & final) | 0
[C8] Project identity/branding | Logo | 1 |  | Done
| Graphics | 1 |  | Done
| Pitch | 1 |  |  |  | done

## Online Channels
|  | Projects Overall Target | Currently Achieved | YEAR 1 - 2025/2026 | [11 empty] | YEAR 2 - 2026/2027 | [11 empty] | YEAR 3 - 2027/2028
|  |  |  | M1 - JAN | M2 - FEB | M3 - MAR | M4 - APR | M5- MAY | M6- JUN | M7 - JUL | M8 - AUG | M9 - SEPT | M10 - OCT | M11 - NOV | M12 - DEC | M13 -JAN | M14 - FEB | M15 - MAR | M16 -APR | M17 - MAY | M18 - JUN | M19 -JUL | M20 -AUG | M21 - SEP | M22 - OCT | M23- NOV | M24 - DEC | M25 -JAN | M26 - FEB | M27-MAR | M28- APR | M29 - MAY | M30 - JUN | M31- JUL | M32 - AUG | M33 - SEPT | M34- OCT | M35 - NOV | M36 - DEC
Webiste
[C1]Website | Visitors |  | 237 | 2 | 51 | 26 | 41 | 36 | 58 | 23
| Pageviews | >1000 | 2069 | 3 | 175 | 792 | 472 | 193 | 132 | 302
| Blog Interactions | >350 | 76 |  |  |  | 2 | 4 | 19 | 51
| Average engagement time per active user |  | 4m 4s | 12 | 57 | 900 | 274 | 98 | 120
Social media
[C6.1]Twitter | Followers |  | 0
| Posts |  | 0
| Views (posts) |  | 0
| Reactions |  | 0
| Comments |  | 0
| Reposts |  | 0
[C6.2]Linkedin | Followers |  | 345 | 28 | 8 | 23 | 29 | 12 | 110 | 135
| Posts |  | 48 | 2 | 2 | 12 | 12 | 6 | 6 | 8
| Reactions |  | 666 | 33 | 28 | 102 | 153 | 121 | 67 | 162
| Comments |  | 6 |  |  | 1 | 2 | 1 | 2 | 0
| Reposts |  | 53 | 10 | 2 | 12 | 14 | 6 | 1 | 8
[C6] Social Media Total | Followers | >1000 followers | 345
| Posts | >800 posts | 53
| Interactions (posts) | >5000 interactions | 837
[C6.3]Zenodo, ResearchGate | Posts |  | 5 |  |  |  | 2 | 1 | 1 | 1
| Views |  | 310 |  |  |  |  | 37 | 102 | 171
| Downloads |  | 112 |  |  |  |  | 28 | 27 | 57
[C5]YouTube (partially) | Subscribers |  | 1 |  |  | 1
| Views | >300 views | 0
| [D10] Promoting Campaigns (partially) | >3 social media campaigns | 3 |  | CRSN Cluster | 1st announcement Data Week |  |  | ECSCI Webinar Series
| [C2] Web/Social Content, blog posts, articles | Y1: >2/month | 10 | 2 | 2 | 1 | 1 |  |  | 4
|  | Y2: >3/month | 0
|  | Y3: >4/month | 0
| [C3] Live audience feedback /live survey in online events | >1 live audience survey | 0
|  | > 50 responders | 0
| [C4] Digital liaisons with projects | >20 backlinks to website | 5 |  |  |  | 5
|  | >10 common posts | 6 |  |  | 4 | 1 |  | 1
Note on B6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Blog Articles = Blogs + Event Recaps, Measure Interaction (Likes, Comments,Reposts) from LinkedIn
Note on A9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Ignore it we don't have X account
Note on B12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: All counts as Interactions Reply: reactions, comments, reposts
Note on B17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: All counts as Interactions
Note on B24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Views & Downloads: Every month deduct previous months result to find the total for the current month

## Media and Videos
| Projects Overall Target | Currently Achieved | YEAR 1 - 2025/2026 | [11 empty] | YEAR 2 - 2026/2027 | [11 empty] | YEAR 3 - 2027/2028
|  |  | M1 - JAN | M2 - FEB | M3 - MAR | M4 - APR | M5- MAY | M6- JUN | M7 - JUL | M8 - AUG | M9 - SEPT | M10 - OCT | M11 - NOV | M12 - DEC | M13 -JAN | M14 - FEB | M15 - MAR | M16 -APR | M17 - MAY | M18 - JUN | M19 -JUL | M20 -AUG | M21 - SEP | M22 - OCT | M23- NOV | M24 - DEC | M25 -JAN | M26 - FEB | M27-MAR | M28- APR | M29 - MAY | M30 - JUN | M31- JUL | M32 - AUG | M33 - SEPT | M34- OCT | M35 - NOV | M36 - DEC
[D8] Open access publications/newsletters | ≥6 scientific open access publications | 2 | [5 empty] | Designing the Furure of Secure Intelligence | Towards Industry 5.0 Reference Architectures for Human-Centric, Trustworthy, and Agentic Cyber-Physical Ecosystems
| ≥6 newsletters | 0
[C9] Press releases, newsletters, and digital briefs | Y1: >3 | 2 |  | 1 - also March | Link
| Y2: >5 | 0
| Y3: >10 (at least 2/pilot) | 0
[D5] Pilot promotional demonstrations/workshops (partially) | >1 demonstration/ pilot video | 0
| >4 workshops /pilot video | 0
[D6] Online and/or Face-toface training/webinars (partially) | 1 user-guide video | 0
[C5] Videos, YouTube channel (partially) | 1 for added value | 0
| 1/pilot | 0
| ≥3 user guides | 0

## Events Count
| Projects Overall Target | Currently Achieved | YEAR 1 - 2025/2026 | [11 empty] | YEAR 2 - 2026/2027 | [11 empty] | YEAR 3 - 2027/2028
|  |  | M1 - JAN | M2 - FEB | M3 - MAR | M4 - APR | M5- MAY | M6- JUN | M7 - JUL | M8 - AUG | M9 - SEPT | M10 - OCT | M11 - NOV | M12 - DEC | M13 -JAN | M14 - FEB | M15 - MAR | M16 -APR | M17 - MAY | M18 - JUN | M19 -JUL | M20 -AUG | M21 - SEP | M22 - OCT | M23- NOV | M24 - DEC | M25 -JAN | M26 - FEB | M27-MAR | M28- APR | M29 - MAY | M30 - JUN | M31- JUL | M32 - AUG | M33 - SEPT | M34- OCT | M35 - NOV | M36 - DEC
[D1] Organization/ participation in events / conferences/ workshops | Demonstrations > 3 | 0
| Final conference > 1 | 0
| Attend: workshops >15 | 4 |  |  |  |  | Cyberchalleng'26-STAM | ICSA'26(HumAIne, TWON) | AIAI26 | SummerSoc
| Attendees: ≥ 450 | 640 |  |  |  |  | 20 | 80 | 500 | 40
| Speakers: ≥ 10 | 4 |  |  |  |  | Data Week | 3D Summit | AIAI26 | SummerSoc - Sandra and Manias
| Follow-up activities per event: ≥ 5 | 0
[D2] Common activities with affiliated projects | >4 common events | 3 |  |  |  |  | Data Week | ICSA'26(HumAIne, TWON) | 3D summit
| >4 posts in CORDIS | 0
[D4] Exhibitions/ demonstrations | >3 exhibitions | 0
| >5 demo days | 1 | [5 empty] | ICSA'26(HumAIne, TWON)
| >90 attendees | 0
[D5] Pilot promotional demonstrations/workshops | >1 demonstration/pilot | 0
| >4 workshops /pilot | 0
[D6] Online and/or Face-toface training/webinars (Non-IT savvy public engagement) (partially) | >3 webinar/trainings | 2 |  |  |  |  | Cyberchalleng'26-STAM |  |  |  | ECSI Webinar Series #2
| >60 attendees | 20 |  |  |  |  | 20
[D7] Clustering, synergies, and common activities with affiliated projects | 6 synergies | 0
| ≥ 6 joint workshops | 1 | [5 empty] | ICSA'26(HumAIne, TWON)
| >5 events | 5 |  |  |  | 16th InfoCom | Data Week'26 | 16th AI Connected Business World | 3D summit | AIAI26
| 5 posts in CORDIS | 0
[D10] Promoting Campaigns (partially) | >3 networking events | 3 | AI Enables Cybersecurity Meet UP |  |  |  | AI Week'26 | 3D Summit
Note on B7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: check speakers from the event list
Note on H7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Gkizelis (mod), Manias (VIGI) - count as 2
Note on K7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: count as 2
Note on B8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: posts on social media, recap mails to the attendants and so on
Note on H17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: students

## Publications
1 | Designing the Future of Secure Intelligence: A Vision for AI-Enabled Cyber-Resilient Ecosystems | link | Conference Paper | OTE/STAM | no open access | CyberAId, ENFORCE, ACT4FOOD, CTIS4NIS, and 5G-TACTIC

## Reported activities
Partner | Description | Activity | Month | Event URL/Reporting Form | Pormotional activities by VIL | Industry, business partners | Innovators | EU Institutions | National authorities | Regional authorities | Local authorities | Civil Society | Citizens | Research communities | Specific end user communities | International organisation (UN body, OECD, etc.) | Other | Investors | Total Reach | EXTRA INFO
4-OTE | AI Enables Cybersecurity Meet UP | Collaboration with EU-funded projects | M1-JAN | https://online.fliphtml5.com/AIEnablesCybersecurity/Bookletv2003/#p=1 |  | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | FALSE |  | FALSE | 700 participants
[7 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE
[7 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE
4-OTE | 3D Circular Summit | Clustering activities | M6-JUN |  |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE | 80 participants
[6 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE
[6 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE
[6 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE
[6 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE
[6 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE
[6 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE
[6 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE
[6 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE
[6 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE
[6 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE
[6 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE
[6 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE
[6 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE
[6 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE
[6 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE
M29-APR
M7-APR
M24-SEP

## Events list
Interested Partners | Status | Event | Dates | Location | Link | Type | Comments | Important Dates | Blog | Speakers | Synergies
STAM/OTE/Cluster | Completed | 11th Workshop on “B5G – Putting Intelligence to the Network Edge” (B5G-PINE 2026) | 16-19 Juy 2026 | Chania, Crete, GR | Link | Workshop | approx 500 participants physical and remote | Paper submission by 5 April |  | Gkizelis | CyberAId, ENFORCE, ACT4FOOD, CTIS4NIS, and 5G-TACTIC
OTE Meetup | Completed | OTE Meetup | 14-01-26 | [5 empty] | Link | Manias, Kugura M, Soldatos, Gkizelis
OTE/GFT/INNOV/Cluster | Completed | Data Week 2026 | 5-6 May |  | Link |  | session to take place on the 5th of May between 11:30-13:00 |  | Link | Manias, Soldatos, Gkizelis | CyberAId, ENFORCE, ACT4FOOD, 5G-TACTIC, CTIS4NIS
OTE/Cluster | Completed | 16 Infocom Security | 29-30 April | Athens, Greece | Link | Conference & Expo | Joint Booth - Share Expenses (VIL paid for VIGI) |  | Link | Gkizelis | CyberAId, ENFORCE, ACT4FOOD, 5G-TACTIC, CTIS4NIS
STAM | Completed | Genoa's Cyber challenge 2026 | 2026-05-19 | Italy | Link | seminar & cyber challenge | 20 participants |  | Link | Gabriele Lanteri (STAM)
DVISOR/UPRC | Completed | Summer Soc | 29 June - 4 July 26 | Crete, Greece | Link | Symposium | 40 participants |  | Link | Manias, Sandra
CRSN Cluster - ECSCI Cluster | Under Discussion | ICTSS 2026 | 13-15 October 26 | Paris, Fr | Link |  |  | Abstract subm. 18 May, Workshop Prop 15 May
CRSN Cluster, VIGI partn: siemens, uprc, D-visor, STAM, ETRA - ECSCI Cluster | Planned | IEEE CloudCom 2026 | 27-29 October 26 | Paris, Fr | Link |  | 17.04 1. agreed to submit a paper, 2. under discussion workshop or session based on how many persons will be available to go | Abst. subm. 30 May, Work Prop 30 May, Manias sto joint paper and jury
DVISOR | Confirmed | University of São Paulo event, during two Computer Science lectures, and at Embraer. | 28 April - 1 May |  |  |  | D-VISOR will present VIGI
DVISOR | Under Discussion | Brazilian Army and to the Dutch Ambassador in São Paulo
GFT | Confirmed | Event? | 2026-04-28 | Milan, Italy |  | Presentation? | pending information
ECSCI Cluster | Under Discussion | Critical Infrastructure Protection & Resilience Europe | 20-22/10/26 | Brussels | Link |  | maybe join booth? I have notified consortium
ECSCI Cluster | Under Discussion | The 7th International Workshop on Cyber-Physical Security for Critical Infrastructures Protection (CPS4CIP 2026) | 14-18 September 2026 | Rome, Italy | Link | paper submission |  | submission: 15.06.26
OTE/Cluster | Completed | 16o AI Connected World 2026, Connect, Protect, Innovate: Greece as a Digital Gateway | 2026-05-27 | Athens, Greece | Link | booth, presentation | CRSN Cluster joint activity - paid by OTE |  |  |  | CyberAId, ENFORCE, ACT4FOOD, 5G-TACTIC, CTIS4NIS
OTE/Cluster | Planned | 3DCircular Summit – ICE – the International Conference on Engineering, Technology, and Innovation (ICE IEEE/ITMC) | 2026-06-22 | Porto, Portugal | Link | Presentation | OTE will participate and present the CRSN Cluster |  |  | Marinakis Achilleas(OTE)
| Under Discussion | HiPEAC | 18-20 January 2027 | Glasgow, UK | Link | Journal paper or workshop |  | by 1st June
ECSCI Cluster - UPRC (Manias, Karamolegkos), STAM (Giulia, Gabriel Lanteri) | Planned | ECSCI Activities - New Webinar Series | July or September |  |  | Webinar Series | we expressed our interest to ECSCI on 18 June, we will have a first presentation of the VIGILANCE
CRSN Cluster | Under Discussion | AI, Data, Robotics Forum (ARDF) 2026 | 13-14 October'26 | Porto, Portugal | Link | Workshop |  | 30 June deadline for workshop information
CRSN Cluster | Under Discussion | EBDVF - European Big Data Value Forum | 30 Sept - 1 Oct'26 | Galway, Ireland | Link | Booth?
UPRC | Completed | ICSA 2026 | 22-26 June | Amsterdam, Netherlands | Link | Workshop (Tutorial/Tech briefing) |  |  |  | Manias | HumAIne, TWON (no official cluster)
ECSCI Cluster | Under Discussion | CIP Week and Critical Infrastructure Protection & Resilience Europe (CIPRE) 2026 | 20-22/10/26 | Brussels | Link | workshop or booth
CRSN CL/OTE | Planned | ADRA Forum 2026 | 13-14/10/26 | Porto, Portugal | Link | workshop | Cyber Resilience by Design: Converging AI, Data, Robotics and Cybersecurity for Europe's Strategic Autonomy | workshop under prep |  |  | CRSN
GFT | Completed | AI Week | 19-20/05/26 | Milan, Italy | Link | booth
Note on A9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: cluster is in favor for that

## Stakeholder Engagement
| Projects Overall Target | Currently Achieved | YEAR 1 - 2025/2026 | [11 empty] | YEAR 2 - 2026/2027 | [11 empty] | YEAR 3 - 2027/2028
|  |  | M1 - JAN | M2 - FEB | M3 - MAR | M4 - APR | M5- MAY | M6- JUN | M7 - JUL | M8 - AUG | M9 - SEPT | M10 - OCT | M11 - NOV | M12 - DEC | M13 -JAN | M14 - FEB | M15 - MAR | M16 -APR | M17 - MAY | M18 - JUN | M19 -JUL | M20 -AUG | M21 - SEP | M22 - OCT | M23- NOV | M24 - DEC | M25 -JAN | M26 - FEB | M27-MAR | M28- APR | M29 - MAY | M30 - JUN | M31- JUL | M32 - AUG | M33 - SEPT | M34- OCT | M35 - NOV | M36 - DEC
[D3] Stakeholder, end user engagement | 75 real market links | 0
| >30 adopters | 0
| >50 testers | 0
[D9] Stakeholder & end-user engagement | >2 events | 0
| >2 appearances | 0
[C10] Stakeholders’ database and engagement tracker | Y1: >1500 entries | 0
| Y2: >2500 entries | 0
| Y3: >4000 entries | 0