## M1-M24 Overview
D=DELIVERABLE | Public | Sensitive
MS=MILESTONE
| YEAR 1 - 2024/2025 | [11 empty] | YEAR 2 - 2025/2026
| M1 - OCT | M2 - NOV | M3 - DEC | M4 - JAN | M5 - FEB | M6 - MAR | M7 - APR | M8 - MAY | M9 - JUN | M10 - JUL | M11 - AUG | M12 - SEP | M13 - OCT | M14 - NOV | M15 - DEC | M16 - JAN | M17 - FEB | M18 - MAR | M19 - APR | M20 - MAY | M21 - JUN | M22 - JUL | M23 - AUG | M24 - SEP
WP1 | YEAR 1 - 2024/2025 M9 - JUN: MS1
T1.1 | YEAR 1 - 2024/2025 M4 - JAN: D1.1 | [14 empty] | D1.4
T1.2 | YEAR 1 - 2024/2025 M6 - MAR: D1.2 | [9 empty] | D1.5
T1.3 | YEAR 1 - 2024/2025 M9 - JUN: D1.3 | [9 empty] | D1.6
WP2 | [11 empty] | MS2 & MS3 | bar: YEAR 1 - 2024/2025 M2 - NOV to YEAR 1 - 2024/2025 M9 - JUN
T2.1 | [11 empty] | D2.1 | [11 empty] | D2.5 | bar: YEAR 1 - 2024/2025 M7 - APR to YEAR 1 - 2024/2025 M9 - JUN
T2.2 | YEAR 1 - 2024/2025 M5 - FEB: OC Kick off; YEAR 1 - 2024/2025 M8 - MAY: OC 1st Cut off | OC 2nd Cut off |  | D2.2 | OC 2nd Cut off
T2.3 | [13 empty] | D2.3 | bar: YEAR 1 - 2024/2025 M4 - JAN to YEAR 1 - 2024/2025 M9 - JUN
T2.4 | [13 empty] | D2.4 | bar: YEAR 1 - 2024/2025 M4 - JAN to YEAR 1 - 2024/2025 M9 - JUN
WP3
T3.1 | [23 empty] | D3.1
T3.2 | [23 empty] | D3.2
T3.3 | YEAR 1 - 2024/2025 M6 - MAR: REPORTING PERIOD 1 | [8 empty] | REPORTING PERIOD 2 | [5 empty] | D3.3
T3.4 | [23 empty] | D3.4
WP4
T4.1 | YEAR 1 - 2024/2025 M3 - DEC: D4.1 | [14 empty] | D4.4
T4.2 | [23 empty] | D4.2
T4.3 | [23 empty] | D4.3
WP5
T5.1 | YEAR 1 - 2024/2025 M4 - JAN: D5.1; YEAR 1 - 2024/2025 M7 - APR: D5.2 |  |  |  | D5.5 | [10 empty] | D5.4
T5.2 | YEAR 1 - 2024/2025 M4 - JAN: D5.3; YEAR 1 - 2024/2025 M6 - MAR: EAB Set up | [14 empty] | D5.6
T5.3
WP6 | [15 empty] | D6.1
Note on F11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The Open Calls (to be reported at D2.2 shall begin officially by the end of February...based on SPLORO (Task Leader) plan: Gantt Chart and Activities for D2.2.xlsx
Note on G25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Accordind to the coordination;s plan, the External Advisory Board (EAB) should be set yp by the end of M6.

## Deliverables' List
Del No | Title | WP | Lead Author | Type | Dissemination Level | Due Date
D1.1 | Roadmap on navigating the complexities of enabling innovative technologies in transitional care | WP1 | 4-SPLORO | Report | Public | M4
D1.2 | Stakeholder Needs Analysis and KPI framework | WP1 | 1-AUTH | Report | Public | M6
D1.3 | EVOVLE2CARE Action Plan | WP1 | 1-AUTH | Report | Public | M9
D1.4 | Roadmap on navigating the complexities of enabling innovative technologies in transitional care - Final | WP1 | 4-SPLORO | Report | Public | M24
D1.5 | Stakeholder Needs Analysis and KPI framework - Final | WP1 | 1-AUTH | Report | Public | M19
D1.6 | EVOVLE2CARE Action Plan - Final | WP1 | 1-AUTH | Report | Public | M19
D2.1 | AccelUP Experimentation Space infrastructure - Final | WP2 | 1-AUTH | OTHER | Public | M12
D2.2 | LLs, Innovators and Researchers Scouting and selection Report | WP2 | 4-SPLORO | Report | Public | M12
D2.3 | Training Program for Living Labs | WP2 | 2-ENoLL IVZW | OTHER | Public | M14
D2.4 | Training Program for Innovators/ Researchers | WP2 | 3-AV | OTHER | Public | M14
D2.5 | AccelUP Experimentation Space infrastructure - Final | WP2 | 1-AUTH | OTHER | Public | M24
D3.1 | Monitoring and Evaluation of the experimentation services | WP3 | 1-AUTH | Report | Public | M24
D3.2 | Lessons Learnt and Policy Recommendations Report | WP3 | 2-ENoLL IVZW | Report | Public | M24
D3.3 | Standardization, Scalability, Replicability and Business Model | WP3 | 3-AV | Report | Public | M24
D3.4 | Commercialization Potential of Innovations | WP3 | 3-AV | Report | Public | M24
D4.1 | Dissemination, Communication and Outreach Strategy and Materials | WP4 | 5-VILABS | Website, patent fillings, videos, etc. | Public | M3
D4.2 | Exploitation and IPR Management | WP4 | 5-VILABS | Report | Public | M24
D4.3 | Clustering with EIT KICs projects and relevant initiatives | WP4 | 2-ENoLL IVZW | Report | Public | M24
D4.4 | Dissemination, Communication and Outreach Strategy and Materials - Final | WP4 | 5-VILABS | Report | Public | M24
D5.1 | Project Management Handbook | WP5 | 1-AUTH | Data Management Plan | Public | M4
D5.2 | Interim Reports | WP5 | 1-AUTH | Report | Public | M7
D5.3 | Technical, IPR and Innovation Management | WP5 | 3-AV | Report | Public | M4
D5.4 | Project Management Handbook - Final | WP5 | 1-AUTH | Report | Public | M24
D5.5 | Interim Reports - Final | WP5 | 1-AUTH | Report | Public | M13
D5.6 | Technical, IPR and Innovation Management - Final | WP5 | 3-AV | Report | Public | M24
D6.1 | OEI - Requirement No. 1 | WP6 | 1-AUTH | ETHICS | Sensitive | M16

## Milestones' List
Mil No | Name | WP | Leader | Means of verification | Due Date
MS1 | Holistic ACCELUP architectural blueprints, functional specifications, and integration roadmap available (first version) | WP1 | 1-AUTH | D1.3(V1) | M9
MS2 | AccelUP platform up and running to onboard Living Labs | WP2 | 1-AUTH | D2.1 (V1) | M12
MS3 | Innovators and LLs onboarded on the AccelUP | WP2 | 4-SPLORO | D2.2 | M12