## M1-M36 overview
MS=MILESTONE | RV=REVIEW
D=DELIVERABLE | Public | Sensitive
RE-SPHERE | YEAR 1 [2026-2027] | [11 empty] | YEAR 2 [2027-2028] | [11 empty] | YEAR 3 [2028-2029]
WP / Task | M1 - JUN | M2 - JUL | M3 - AUG | M4 - SEP | M5 - OCT | M6 - NOV | M7 - DEC | M8 - JAN | M9 - FEB | M10 - MAR | M11 - APR | M12 - MAY | M13 - JUN | M14 - JUL | M15 - AUG | M16 - SEP | M17 - OCT | M18 - NOV | M19 - DEC | M20 - JAN | M21 - FEB | M22 - MAR | M23 - APR | M24 - MAY | M25 - JUN | M26 - JUL | M27 - AUG | M28 - SEP | M29 - OCT | M30 - NOV | M31 - DEC | M32 - JAN | M33 - FEB | M34 - MAR | M35 - APR | M36 - MAY
WP1 | YEAR 1 [2026-2027] M1 - JUN: MS1 |  |  | MS2 | [5 empty] | RV1 | [17 empty] | RV2
T1.1 | YEAR 1 [2026-2027] M3 - AUG: D1.1
T1.2
T1.3 | [17 empty] | D1.2
T1.4 | YEAR 1 [2026-2027] M6 - NOV: D1.3
WP2 | YEAR 1 [2026-2027] M8 - JAN: MS3 | [14 empty] | MS4
T2.1 | bar: YEAR 1 [2026-2027] M2 - JUL to YEAR 1 [2026-2027] M8 - JAN
T2.2 | bar: YEAR 1 [2026-2027] M2 - JUL to YEAR 1 [2026-2027] M8 - JAN
T2.3 | bar: YEAR 1 [2026-2027] M2 - JUL to YEAR 1 [2026-2027] M8 - JAN
T2.4 | [9 empty] | D2.1 | bar: YEAR 1 [2026-2027] M2 - JUL to YEAR 1 [2026-2027] M9 - FEB
T2.5 | [29 empty] | D2.2
WP3 | bar: YEAR 1 [2026-2027] M8 - JAN to YEAR 1 [2026-2027] M9 - FEB
T3.1 | [11 empty] | D3.1 | bar: YEAR 1 [2026-2027] M8 - JAN to YEAR 1 [2026-2027] M9 - FEB
T3.2 | [17 empty] | D3.2
T3.3
WP4 | [16 empty] | MS5 | [18 empty] | MS6
T4.1 | [17 empty] | D4.1
T4.2
T4.3 | [35 empty] | D4.2 / D4.3
WP5 | YEAR 1 [2026-2027] M8 - JAN: MS7
T5.1 | bar: YEAR 1 [2026-2027] M4 - SEP to YEAR 1 [2026-2027] M9 - FEB
T5.2 | bar: YEAR 1 [2026-2027] M7 - DEC to YEAR 1 [2026-2027] M9 - FEB
T5.3 | [19 empty] | D5.1
T5.4 | [33 empty] | D5.2
T5.5
WP6 | [31 empty] | MS8 |  | MS9
T6.1 | [19 empty] | D6.1
T6.2
T6.3
T6.4 | [33 empty] | D6.2
WP7 | [15 empty] | MS10 | [19 empty] | MS11
T7.1
T7.2 | [23 empty] | D7.1
T7.3
T7.4 | [35 empty] | D7.2
WP8 | YEAR 1 [2026-2027] M6 - NOV: MS12 | [14 empty] | MS13 | [9 empty] | MS14
T8.1 | [17 empty] | D8.1
T8.2 | [19 empty] | D8.2 | bar: YEAR 1 [2026-2027] M3 - AUG to YEAR 1 [2026-2027] M9 - FEB
T8.3 | bar: YEAR 1 [2026-2027] M3 - AUG to YEAR 1 [2026-2027] M9 - FEB
T8.4 | [33 empty] | D8.3
T8.5 | bar: YEAR 1 [2026-2027] M3 - AUG to YEAR 1 [2026-2027] M9 - FEB
WP9 | YEAR 1 [2026-2027] M1 - JUN: D9.1 | [7 empty] | D9.2
Reporting periods | YEAR 1 [2026-2027] M1 - JUN: 1ST REPORTING PERIOD | [9 empty] | 2ND REPORTING PERIOD

## Deliverables' list
Del No | Title | WP | Lead Beneficiary | Type | Dissemination Level | Due Date
D1.1 | Project Handbook and Management Plan | WP1 | 1 - AUTh | R — Document, report | PU - Public | M3
D1.2 | Ethical Management and Regulatory Compliance Handbook | WP1 | 12 - VIL | R — Document, report | PU - Public | M18
D1.3 | Data Management Plan (DMP) | WP1 | 12 - VIL | R — Document, report | PU - Public | M6
D2.1 | Interdisciplinary Research Guidelines and Methodological Framework | WP2 | 3 - UNSA | R — Document, report | PU - Public | M10
D2.2 | Interdisciplinary Synthesis & Publication | WP2 | 1 - AUTh | R — Document, report | PU - Public | M30
D3.1 | Geo-Referenced Atlas of SHPs in SEE | WP3 | 2 - WCC | OTHER | PU - Public | M12
D3.2 | Field Report on Ritual Use and Spatial Practices | WP3 | 2 - WCC | R — Document, report | PU - Public | M18
D4.1 | Visual Narrative Series | WP4 | 13 - ACM | OTHER | PU - Public | M18
D4.2 | Dual Virtual Exhibition Platform | WP4 | 9 - CERTH | OTHER | PU - Public | M36
D4.3 | On-site Traveling Exhibition Kit | WP4 | 13 - ACM | OTHER | PU - Public | M36
D5.1 | Prototype App & Final Release of RE-SPHERE Digital Ecosystem | WP5 | 12 - VIL | OTHER | PU - Public | M20
D5.2 | Knowledge Graphs, Foresight Tools & Sustainability Roadmap | WP5 | 9 - CERTH | OTHER | PU - Public | M34
D6.1 | SHP Impact Assessment Framework and Report | WP6 | 6 - uni.lu | R — Document, report | PU - Public | M20
D6.2 | Policy Report on the Operationalization of SHPs as platforms for cultural peace economies | WP6 | 6 - uni.lu | R — Document, report | PU - Public | M34
D7.1 | Modular Training Package on Interfaith Dialogue and Conflict Mediation | WP7 | 10 - FCA | OTHER | PU - Public | M24
D7.2 | Digital Diplomacy Manual for SHPs' Management | WP7 | 1 - AUTh | OTHER | PU - Public | M36
D8.1 | Dissemination, Communication and Exploitation Plan | WP8 | 12 - VIL | R — Document, report | PU - Public | M18
D8.2 | Replication & Sustainability Guidebook | WP8 | 12 - VIL | R — Document, report | PU - Public | M20
D8.3 | KLI Youth Series Compendium | WP8 | 12 - VIL | OTHER | PU - Public | M34
D9.1 | OEI - POPD - H - Requirement No. 1 | WP9 | 1 - AUTh | ETHICS | SEN - Sensitive | M1
D9.2 | OEI - H - POPD - Requirement No. 2 | WP9 | 1 - AUTh | ETHICS | SEN - Sensitive | M17

## Milestones' list
Mil No | Name | WP | Leader | Means of verification | Due Date
MS1 | Successful organization of the kick-off Meeting | WP1 | 1 - AUTh | Successful completion of the kick-off meeting (Meeting Minutes) | M1
MS2 | Establishment of GELSCA Framework available | WP1 | 12 - VIL | D1.3 Available | M12
MS3 | Draft of Interdisciplinary & Intersectional Framework | WP2 | 3 - UNSA | Successful delivery of a preliminary framework report for gathering internal feedback, validated internally by consortium partners. | M8
MS4 | Successful Implementation of Open Lab in Thessaloniki | WP2 | 1 - AUTh | Successful organization and delivery of the Open Lab in Thessaloniki. Feedback and validation integrated into RE-SPHERE framework. | M24
MS5 | Implementation of Youth Co-creation Lab | WP4 | 11 - NIMOH | Three-day workshop successfully delivered in Ohrid with 15–20 youth participants producing original artistic content. | M17
MS6 | Opening of On-Site Exhibition in Athens (ACM) | WP4 | 13 - ACM | Six-month exhibition (3 months at ACM, 3 months at NIMOH) successfully launched at ACM, featuring visual documentation and youth artworks. | M36
MS7 | User Needs & Requirements Finalized | WP5 | 9 - CERTH | Consolidated report of user requirements collected from workshops and stakeholder consultations (youth, educators, pilgrims, researchers, policymakers). | M8
MS8 | Cultural Peacebuilding Policy Framework | WP6 | 6 - uni.lu | First full draft of the “Sustainable Peace through Sustainable Economy of SHPs” framework (guidelines, toolkits, indicators) successfully circulated for consortium/AB review. | M32
MS9 | Cultural Peacebuilding Policy Framework Pilot Activities completed | WP6 | 7 - UzhNU | Usability/adaptability assessments executed across diverse SHP contexts; feedback captured via standardized instruments. | M34
MS10 | Stakeholder Map & Needs Baseline Published | WP7 | 2 - WCC | Country-by-country stakeholder registers, role typologies, gaps, and priority needs successfully completed and approved. | M16
MS11 | Final Digital Diplomacy Toolkit Released | WP7 | 1 - AUTh | Modular, multilingual toolkit (manual and online interface) published with trainer guides, policy briefs, and integration links to WP5 tools. | M36
MS12 | Exploitation & Sustainability Strategy Approved | WP8 | 12 - VIL | Clear pathways for exploitation and long-term sustainability successfully validated by consortium. | M6
MS13 | First Youth-Oriented Digital Content Released | WP8 | 12 - VIL | First set of RE-SPHERE Shots, podcasts, or meme challenges successfully published. | M24
MS14 | Replication & Sustainability Guidebook Released | WP8 | 12 - VIL | Final version published and successfully circulated among stakeholders. | M34

## Reviews & RPs
Reviews
Review No | Timing (month) | Location | Comments
RV1 | M18 | TBD
RV2 | M36 | TBD
Reporting Periods
RP No | From (month) | To (month) | Type | Deadline
RP1 | M1 | M18 | Periodic report | 60 days after end of reporting period
RP2 | M19 | M36 | Periodic report | 60 days after end of reporting period